## Phase I
Development of Phase-I
Phase-I
Module | Sub Module | Start Date | End Date | Development Responsibity | Status | Remarks
Admin Panel | User Policies and Rules | 2016-05-16 | 2016-05-20 | Himanshu/Vimal | done
| Security | 2016-05-16 | 2016-05-20 | Himanshu/Vimal | In progress
| Home | 2016-05-16 | 2016-05-20 | Himanshu/Vimal | today
| Change Year | 2016-05-16 | 2016-05-20 | Himanshu/Vimal | done
| Employee Portal Panel | 2016-05-20 | 2016-05-30 | Hariom/Vimal
| My Profile | 2016-05-23 | 2016-05-26 | Himanshu/Vimal
| Company Annoucement | 2016-05-26 | 2016-05-30 | Himanshu/Vimal
| Departmental Notification | 2016-05-26 | 2016-05-30 | Himanshu/Vimal
| Message Admin Panel | 2016-05-26 | 2016-05-30 | Himanshu/Vimal
| Mail Notification | 2016-05-26 | 2016-05-30 | Himanshu/Vimal
| Manage Alert | 2016-05-26 | 2016-05-30 | Himanshu/Vimal
| New Opening | 2016-05-26 | 2016-05-30 | Himanshu/Vimal
| Employee Recognition | 2016-05-26 | 2016-05-30 | Himanshu/Vimal
| Attendance Panel | 2016-05-30 | 2016-06-03 | Himanshu/Vimal
| Workflow Manager | 2016-06-03 | 2016-06-07 | Himanshu/Vimal
| Leave Panel | TBD | TBD | Himanshu/Vimal
| Log Reports | 2016-07-01 | 2016-07-01 | Himanshu/Vimal
EIP | Organization Structures | 2016-05-16 | 2016-05-20 | Hariom/Vimal
| My Profie | 2016-05-23 | 2016-06-01 | Subodh/Vimal
| My Team | 2016-05-23 | 2016-06-01 | Subodh/Vimal
| Add Employee | 2016-05-23 | 2016-06-01 | Subodh/Vimal
| Edit Employee | 2016-05-23 | 2016-06-01 | Subodh/Vimal
| Download Employee Master | 2016-05-23 | 2016-06-01 | Subodh/Vimal
| Employee Upload | 2016-05-23 | 2016-06-01 | Subodh/Vimal
Attendance | Out on work Requrest | 2016-06-02 | 2016-06-03 | Subodh/Hariom/Vimal
| Mark Past Attendance | 2016-06-04 | 2016-06-06 | Subodh/Hariom/Vimal
| Approval of out on work Requrest | 2016-06-06 | 2016-06-08 | Subodh/Hariom/Vimal
| Approval Mark Past Attendance | 2016-06-06 | 2016-06-08 | Subodh/Hariom/Vimal
| My Calender | 2016-06-07 | 2016-06-13 | Himanshu/Vimal
| My Team Calender | 2016-06-07 | 2016-06-13 | Himanshu/Vimal
| My Team Attendance Summary | 2016-06-07 | 2016-06-13 | Himanshu/Vimal
| My out on work Requrest | 2016-06-09 | 2016-06-10 | Subodh/Hariom/Vimal
| All out on work Requrest | 2016-06-09 | 2016-06-10 | Subodh/Hariom/Vimal
| My Past attendance Request | 2016-06-09 | 2016-06-10 | Subodh/Hariom/Vimal
| All Past attendance Request | 2016-06-09 | 2016-06-10 | Subodh/Hariom/Vimal
| Manage Shift | 2016-06-14 | 2016-06-23 | Himanshu/Vimal
| Manager Shift Pattern | 2016-06-14 | 2016-06-23 | Himanshu/Vimal
| Shift Allocation | 2016-06-14 | 2016-06-23 | Himanshu/Vimal
| Manage Roaster | 2016-06-13 | 2016-06-20 | Subodh/Hariom/Vimal
| Attedance Upload | 2016-06-13 | 2016-06-20 | Subodh/Hariom/Vimal
| Roaster Upload | 2016-06-13 | 2016-06-20 | Subodh/Hariom/Vimal
Leave | TBD | TBD | TBD | Himanshu/Subodh/Vimal
Reports | Profile Reports | TBD | TBD | Himanshu/Subodh/Vimal
| Attendance Reports | TBD | TBD | Himanshu/Subodh/Vimal
| Leave Reports | TBD | TBD | Himanshu/Subodh/Vimal
| MIS Reports | TBD | TBD | Himanshu/Subodh/Vimal
| Payroll Reports | TBD | TBD | Himanshu/Subodh/Vimal
| Customized reports | TBD | TBD | Himanshu/Subodh/Vimal
GO LIVE ON 1st July 2016

## Phase II
Phase-II
Policies & Forms | Policies
Policies & Forms | Upload Policies
Policies & Forms | Forms
Policies & Forms | Upload Forms
Admin Panel | Component Setup
Admin Panel | Formula Setup
Payroll
Seperation
Help | Tutorial of the portal | Vimal
Help | Shortcut of the commands | Vimal/Subodh
HelpDesk | Will be link to the HelpDesk portal | Subodh/Vimal
Tools | Import
Tools | Export